## const_CMY_Area
GIS DATA CHANGES
EPL GIS DATA CHANGE
Feature Class Changed: |  |  | Data Owner Name: | Data Lead Name: |  | Date Spread Sheet Completed:
const_CMY_Area | [5 empty] | 2026-02-25
Feature Class Updated Details |  |  |  |  | Feature Class Record Count (FC IN/FC OUT): | (0/0) |  | Add | Delete | Modify
Work Package/Segment | What was updated | Number of Features | Feature Location | Add/Delete/Modify | Update Date | Change Reason | Person Requesting Change | 4 | 0 | 0
Segment 3 | Added Kelbaker Road 1 Material Staging Yard | 1 | 35.257386 N, 116.058989 W | Add | 2025-10-18 | Requested by project team | David de Leon, Conrad Mulligan
Segment 3 | Added Kelbaker Road 4 Material Staging Yard | 1 | 35.255751 N, 115.982428 W | Add | 2025-10-18 | Requested by project team | David de Leon, Conrad Mulligan
Segment 3 | Added Cima Road Rock Circle Material Staging Yard | 1 | 35.423397 N, 115.646435 W | Add | 2025-10-18 | Requested by project team | David de Leon, Conrad Mulligan
Segment 3 | Added Cima Road Tree Square Material Staging Yard | 1 | 35.425883 N, 115.644914 W | Add | 2025-10-18 | Requested by project team | David de Leon, Conrad Mulligan

## const_Construction_Area
GIS DATA CHANGES
EPL GIS DATA CHANGE
Feature Class Changed: |  |  | Data Owner Name: | Data Lead Name: |  | Date Spread Sheet Completed:
const_Construction_Area | [5 empty] | 2026-02-25
Feature Class Updated Details |  |  |  |  | Feature Class Record Count (FC IN/FC OUT): | (0/0) |  | Add | Delete | Modify
Work Package/Segment | What was updated | Number of Features | Feature Location | Add/Delete/Modify | Update Date | Change Reason | Person Requesting Change | 5 | 1 | 0
Segment 3 | Added helicopter landing zone | 1 | 35.255229 N, 115.982895 W | Add | 2026-02-20 | Construction material yard was missing HLZ | Conrad Mulligan
Segment 3 | Added helicopter landing zone | 1 | 35.257372 N, 116.059748 W | Add | 2026-02-20 | Construction material yard was missing HLZ | Conrad Mulligan
Segment 3 | Added helicopter landing zone | 1 | 35.288879 N, 116.081382 W | Add | 2026-02-20 | Construction material yard was missing HLZ | Conrad Mulligan
Segment 3 | Added helicopter landing zone | 1 | 35.423493 N, 115.646634 W | Add | 2026-02-20 | Construction material yard was missing HLZ | Conrad Mulligan
Segment 3 | Added helicopter landing zone | 1 | 35.423537 N, 115.646677 W | Add | 2026-02-20 | Construction material yard was missing HLZ | Conrad Mulligan
Segment 4 | Deleted helicopter landing zone | 1 | 35.250261 N, 115.512410 W | Delete | 2026-02-20 | HLZ was left over after material yard deleted | Conrad Mulligan

## proj_AccessRoad_Line
GIS DATA CHANGES
EPL GIS DATA CHANGE
Feature Class Changed: |  |  | Data Owner Name: | Data Lead Name: |  | Date Spread Sheet Completed:
proj_AccessRoad_Line | [5 empty] | 2026-02-25
Feature Class Updated Details |  |  |  |  | Feature Class Record Count (FC IN/FC OUT): | (0/0) |  | Add | Delete | Modify
Work Package/Segment | What was updated | Number of Features | Feature Location | Add/Delete/Modify | Update Date | Change Reason | Person Requesting Change | 0 | 22 | 56
Segment 1 | Deleted existing access road | 1 | 34.427141 N, 117.163775 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 1 | Deleted overland travel | 1 | 34.643581 N, 116.575017 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 1 | Deleted existing access road | 1 | 34.667462 N, 116.532054 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 1 | Modified existing access road | 1 | 34.684390 N, 116.499712 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 1 | Deleted existing access road | 1 | 34.689699 N, 116.494515 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 1 | Deleted existing access road | 1 | 34.713801 N, 116.465569 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 2 | Deleted overland travel | 1 | 34.464599 N, 117.033436 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 2 | Deleted overland travel | 1 | 34.465513 N, 117.030858 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 2 | Deleted overland travel | 1 | 34.467663 N, 117.024615 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 2 | Deleted existing access road | 1 | 34.637669 N, 116.582420 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified overland travel | 1 | 35.070862 N, 115.876799 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.076224 N, 115.864133 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.076872 N, 115.860495 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.077043 N, 115.860786 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.077323 N, 115.856822 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.078333 N, 115.856840 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.079329 N, 115.848005 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.079801 N, 115.851032 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.080532 N, 115.848192 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.081463 N, 115.849033 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.081588 N, 115.849565 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.081955 N, 115.846540 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.082019 N, 115.844344 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Deleted existing access road | 1 | 35.086523 N, 115.841331 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Deleted existing access road | 1 | 35.086712 N, 115.841383 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.086845 N, 115.842221 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.089361 N, 115.838985 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.092143 N, 115.833983 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.095216 N, 115.830420 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.095891 N, 115.829085 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.097874 N, 115.825534 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified overland travel | 1 | 35.097885 N, 115.825995 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Deleted duplicate overland travel | 1 | 35.097885 N, 115.825995 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.097972 N, 115.825369 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.104311 N, 115.816782 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified overland travel | 1 | 35.104595 N, 115.816070 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.105882 N, 115.814369 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | 35.107156 N, 115.812869 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road and changed to overland travel | 1 | 35.108589 N, 115.808843 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Deleted overland travel | 1 | 35.116684 N, 115.793415 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Changed existing access road to overland travel | 1 | 35.126351 N, 115.774305 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Deleted existing access road | 1 | 35.128749 N, 115.769813 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road and changed to overland travel | 1 | 35.161181 N, 115.707232 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Deleted overland travel | 1 | 35.185736 N, 115.658656 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | From 35.080741 N, 115.841647 W to 35.091971 N, 115.833097 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 3 | Modified existing access road | 1 | From 35.088027 N, 115.829713 W to 35.104496 N, 115.818016 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Changed existing access road to overland travel | 1 | 34.880590 N, 116.237916 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Changed existing access road to overland travel | 1 | 34.894707 N, 116.210915 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Deleted overland travel | 1 | 34.905564 N, 116.201298 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified overland travel | 1 | 35.014492 N, 116.056093 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified existing access road | 1 | 35.027862 N, 116.029399 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Deleted overland travel | 1 | 35.027885 N, 116.029363 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified overland travel | 1 | 35.078685 N, 115.845923 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified overland travel | 1 | 35.079909 N, 115.842703 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified overland travel | 1 | 35.080600 N, 115.839310 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified existing access road | 1 | 35.081097 N, 115.834734 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified overland travel | 1 | 35.082685 N, 115.831941 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Deleted overland travel | 1 | 35.087563 N, 115.829840 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified overland travel | 1 | 35.093250 N, 115.826559 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified existing access road | 1 | 35.101728 N, 115.818216 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified overland travel | 1 | 35.102946 N, 115.818523 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified existing access road | 1 | 35.103386 N, 115.817702 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified existing access road | 1 | 35.106776 N, 115.812381 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified existing access road | 1 | 35.107636 N, 115.809903 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified existing access road | 1 | 35.107757 N, 115.808474 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Deleted overland travel | 1 | 35.252974 N, 115.512414 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Deleted overland travel | 1 | 35.253116 N, 115.512319 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Deleted existing access road | 1 | 35.253355 N, 115.512677 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified existing access road | 1 | 35.258244 N, 115.498697 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Deleted existing access road | 1 | 35.277630 N, 115.474943 W | Delete | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Changed existing access road to overland travel | 1 | 35.313397 N, 115.425468 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Changed existing access road to overland travel | 1 | 35.343702 N, 115.383138 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Changed existing access road to overland travel | 1 | 35.433982 N, 115.257461 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified existing access road | 1 | From 35.076319 N, 115.864181 W to 35.088032 N, 115.829711 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified existing access road | 1 | From 35.091977 N, 115.833130 W to 35.099297 N, 115.823342 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified existing access road | 1 | From 35.104491 N, 115.818072 W to 35.108142 N, 115.810314 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 4 | Modified existing access road | 1 | From 35.108142 N, 115.810314 W to 35.111030 N, 115.804224 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson
Segment 5 | Modified existing access road | 1 | 35.793164 N, 115.005319 W | Modify | 2026-02-20 | Discussions w/NPS and SWCA | Conrad Mulligan, Matthew DeFreese, Alex Wesson