## Table 1
ATTACHMENT 1
Construction Phase | Comment/Notes | How to Address | SCE Comments
Staging Areas | CalEEMod missing two water trucks trips as haul trucks | Adjust accordingly or provide justification of discrepancy | See RTC for DR1-1. No adjustments to the CalEEMod run was needed to address this comment.
Road Work | CalEEMod missing excavator. | Adjust accordingly or provide justification of discrepancy | Comment noted. The excavator was mistakenly left out of the CalEEMod run and has been added to the updated model run.
Road Work | CalEEMod missing two water truck trips as haul trucks | Adjust accordingly or provide justification of discrepancy | See RTC for DR1-1. No adjustments to the CalEEMod run was needed to address this comment.
Install TSP H-frame Foundations | Onsite trucks should be 20 miles instead of 16.8 miles | Adjust accordingly or provide justification of discrepancy | See RTC for DR1-1. No adjustments to the CalEEMod run was needed to address this comment.
TSP H-frame Haul | Onsite trucks should be 20 miles instead of 23.3 miles | Adjust accordingly or provide justification of discrepancy | See RTC for DR1-1. No adjustments to the CalEEMod run was needed to address this comment.
TSP H-frame Assembly | CalEEMod missing water truck trip as haul truck A8:E33 | Adjust accordingly or provide justification of discrepancy | See RTC for DR1-1. No adjustments to the CalEEMod run was needed to address this comment.
TSP H-frame Erection | Onsite trucks should be 20 miles instead of 10 miles | Adjust accordingly or provide justification of discrepancy | See RTC for DR1-1. No adjustments to the CalEEMod run was needed to address this comment.
Install/Remove Conductor/OHGW | CalEEMod estimated days associated with subphase 8a through 8d of 29, 102, 134, and 202 do not match Table 3.6-1 of 103, 203, 267, and 403 days, respectively. | Adjust accordingly or provide justification of discrepancy | See RTC for DR1-1 for an explanation of the duration of each subphase. For subphase 8a, the duration was mistakenly shortened by one additional month. The CalEEMod model was adjusted to 52 days for subphase 8a.
Install/Remove Conductor/OHGW | CalEEMod has two backhoe/front loader and Table 3.6-1 has one backhoe/front loader | Adjust accordingly or provide justification of discrepancy | See RTC for DR1-1. No adjustments to the CalEEMod run was needed to address this comment.
Install/Remove Conductor/OHGW | CalEEMod has 14 pieces of equipment, Table 3.6-1 suggests 7 pieces of equipment | Adjust accordingly or provide justification of discrepancy | Table 3.6-1 indicates that there are 6 pieces of ground equipment and 1 helicopter. As indicated in the RTC for DR.1-1, the number of crews (and thus number of equipment) were doubled while the duration was halved. A duplicate of the conductor splicing rig was generated in CalEEMod mistakenly and thus the revised CalEEMod run now presentes 12 pieces of ground equipment.
Install/Remove Conductor/OHGW | CalEEMod has 8 onsite trucks in Phase 8b, 2 onsite trucks in Phase 8c, and 16 onsite trucks in Phase 8d, but Table 3.6-1 has a total of 15 trucks within the four subphases. | Adjust accordingly or provide justification of discrepancy | Table 3.6-1 shows a total of 16 trucks within the four subphases (2 wire truck/trailers, 1 jet A fuel truck, 1 helicopter support truck in subphase 8B, 1 dump truck in subphase 8C, and 1 3/4- ton truck 2 1-ton truck, 1 static truck/tensioner, 1 manlift bucket truck, 1 boom crane truck, 2 semi-tractor truck and 2 lowboy truck/trailer). As indicated in RTC for DR1-1, the number of crews (and thus number of pieces of equipment) were doubled while the duration was halved.
Install/Remove Conductor/OHGW | Onsite trucks should be 20 miles instead of 5.5, 30, and 27.5 miles depending on subphase. | Adjust accordingly or provide justification of discrepancy | See RTC for DR1-1. No adjustments to the CalEEMod run was needed to address this comment.
Install/Remove Conductor/OHGW | Worker trips should be 25 miles instead of 18.5 miles. | Adjust accordingly or provide justification of discrepancy | Worker trips lengths are set to 25 miles. For the instances that have 18.5 miles listed, the number of workers is 0 and do not impact the calculations.
Install/Remove Guard Structure | Onsite trucks should be 20 miles instead of 26 miles. | Adjust accordingly or provide justification of discrepancy | See RTC for DR1-1. No adjustments to the CalEEMod run was needed to address this comment.
Modify Existing Structure | Onsite trucks should be 20 miles for 10a and 10b instead of 20 and 30 miles. | Adjust accordingly or provide justification of discrepancy | See RTC for DR1-1. No adjustments to the CalEEMA9:E33od run was needed to address this comment.