## Sheet1
Comparison of Maximum Day Activities - Project and Alternatives
2016
Project | Alternative Q3 | Alternative Q4 | Alternative Q5 | Alternative Q6 | Alternative Q7
Segment A | Segment A | Segment A | Segment A | Segment A | Segment A
Foundation Excavation | Wire Stringing | Site Preparation and Road Construction | Wire Stringing | Wire Stringing | Wire and Structure Removals
Foundation Rebar |  | Wire and Structure Removals | Cleanup and Restoration | Cleanup and Restoration | Foundation Construction
Foundation Concrete |  | Foundation Construction
Segment B | Segment B | Segment B | Segment B | Segment B | Segment B
Trenching | Excavation and Install Vaults and Trench | Excavation and Install Vaults and Trench | Excavation and Install Vaults and Trench | Excavation and Install Vaults and Trench | Excavation and Install Vaults and Trench
Backfill/Paving | Cleaning and Proving Ducts | Cleaning and Proving Ducts | Cleaning and Proving Ducts | Cleaning and Proving Ducts | Ducts Through Bridge
| Cabling |  | Bridge Attachments | Bridge Attachments
|  |  | Cabling | Cabling
Segment C | Segment C | Segment C | Segment C | Segment C | Segment C
Road/Pad Maintenance | Foundation Construction | No Activity | No Activity | No Activity | Site Preparation and Road Construction
Segment D | Segment D | Segment D | Segment D | Segment D | Segment DF
Build Retaining Wall | No Activity | No Activity | No Activity | No Activity | No Activity
Segment E | Segment E | Segment E | Segment E | Segment E | Segment E
No Activity | No Activity | No Activity | No Activity | No Activity | Excavate and Install Trench
2017
Project | Alternative Q3 | Alternative Q4 | Alternative Q5 | Alternative Q6 | Alternative Q7
Segment A | Segment A | Segment A | Segment A | Segment A | Segment A
Wire Stringing/Sagging/Clipping | No Activity | No Activity | No Activity | No Activity | Wire Stringing
Segment B | Segment B | Segment B | Segment B | Segment B | Segment B
Cabling | Cabling | Cabling | Cabling | Cabling | Cabling
Splice and Termination
Segment C | Segment C | Segment C | Segment C | Segment C | Segment C
No Activity | Cleanup and Restoration | No Activity | No Activity | No Activity | No Activity
Segment D | Segment D | Segment D | Segment D | Segment D | Segment DF
Steel Hauling | No Activity | No Activity | No Activity | No Activity | Wire Stringing
Steel Structure Assembly
Segment E | Segment E | Segment E | Segment E | Segment E | Segment E
No Activity | No Activity | No Activity | No Activity | No Activity | Cleaning and Proving Ducts
Cabling