Paradise Area Reinforcement Project

Mitigation Monitoring Report No. 13

Project Memorandum  

Paradise Area Reinforcement Project
To:
Roosevelt Grant, CPUC

From:
Matt Fagundes, Deputy Project Manager

Date:
March 7, 2002

Re: 
Mitigation Monitoring Report No. 13: February 2, 2002 – February 28, 2002

The following descriptions of compliance and monitoring activities for the Paradise Area Reinforcement Project are from project summary reports supplied to Aspen Environmental Group (Aspen) by PG&E Co. (PG&E) and personal communications between Matt Fagundes of Aspen and Armen Keochekian of Essex Environmental (PG&E Environmental Inspector).  

Summary

This Mitigation Monitoring Report provides a general update of construction activities associated with the Paradise Area Reinforcement Project.  It also describes mitigation measures that have been implemented to date in accordance with the Project’s Mitigated Negative Declaration.  This report represents all activities from February 2, 2002 to February 28, 2002.  

Work conducted during this time period was primarily associated with stringing the power line on the previously installed tubular steel poles along segments 1, 2, and 3, installation of cathodic protection on poles in Segment 4, and removal of travelers from poles 39 through 62.  PG&E has indicated that construction activities associated with the power line are anticipated to be complete by March 8, 2002.  However, it is anticipated that PG&E will be conducting clean-up activities along the project right-of-way, including restoration to the Trailway, throughout March.  

Construction Activities

Power Line Construction

During the week of February 4, the power line crew continued to prepare the southern portion of the route (segments 1, 2, and 3) for sock line stringing activities.  Small crews worked at the pull site on Skyway, the pull site near the tap at the southernmost point of the project, and at various poles throughout segments 1, 2, and 3.  A small crew also worked on cleanup activities along the Paradise Memorial Trailway.  All activities associated with stringing conductor along segments 1, 2, and 3, were completed during the week of February 11.  Once the conductor was secured in place to the poles, PG&E dismantled the equipment that was used at the two pull sites and hauled it to an off-site location.  Power line construction continued the week of February 18 with small crews that worked at various pole locations along the project route.  Crews installed cathodic protection to poles between Neal Road and Foster Road in Segment 4 and removed travelers and secured the conductors from poles 39 through 62 along the southern portion of the route.  PG&E anticipates that the remainder of the power line will be completed by March 8.  PG&E plans to energize the entire line on March 8, weather and access conditions permitting.

Paradise Substation Upgrades 

Conduit, grounds, and foundation work has been completed at the substation.  Interior electrical work is approximately 75 percent complete.  Interior and exterior substation upgrades will continue through March with a crew of 5 to 8 workers.  All activities have been limited to the fenced substation yard within PG&E’s property. 

Mitigation Highlights

Applicant Proposed Measures 5-2 and 5-8.  PG&E’s vegetation management group was on-site the week of February 18 to inspect the trees along Segments 4 and 5 to ensure compliance with State and local regulations governing the proximity of the power lines to adjacent trees.  Sixty-eight trees were identified as needing additional trimming or removal.  Of the 68 trees, 27 would require removal and 41 would need to be trimmed or topped.  The majority of the trees are gray pines, however, there are also black oak and ponderosa pines that will be trimmed or removed.  

PG&E’s biologist surveyed each tree for potential bat habitat and three trees were identified as exhibiting characteristics that could provide habitat for roosting bats. These trees were marked with yellow and black-stripped ribbon indicating that they needed to be treated using the established bat tree removal protocol prior to removing or trimming the trees.  PG&E’s Senior Forester, who has performed the bat tree removal protocol in the past, performed the protocol prior to the tree trimming and removal work that was conducted during the week of February 25.  With regard to potential impacts to nesting birds, all tree trimming and removal work was completed prior to the start of the nesting season, which began on March 1. 

Applicant Proposed Measure 5-9.  A crew worked on installing cathodic protection to the poles in Segment 4, between Neal Road and Foster Road.   The elderberry plants were protected in this area using a block and tackle to ensure that the cathodic wire would not fall on the plants. The procedure took place without incident. 
Measures Completed to Date

III-1:
Dispose plant debris in a manner other than controlled burning

V-1:
Cultural resources training for project workers

MM 5-1:
Survey for special status plants

MM 5-3:
Preparation of Amphibian Habitat Assessment

MM 5-5 and 5-7:
Preparation of Vegetation Management, Erosion Control and Restoration Plan

MM 5-8:
Survey for pallid bat roosts

MM 5-9
Avoid and protect the valley elderberry longhorn beetle.

MM 6-1:
Train depot shall be spanned by the power line

MM 6-4, V-2, and MM 5-10: Surveys for laydown area on Neal Road

MM 7-1:
Insure that construction impacts to other utilities are less than significant

MM 8-1:
Evaluate slope stability to select pole locations

MM 9-2:
Hazardous substances and control training for project workers

MM 9-4 and 12-4: Revise the Paradise Substation Spill Prevention, Countermeasure, and Control Plan.

MM 10-1:
Notify landowners adjacent to project prior to construction

MM 11-7:
Transformers to meet or exceed 69 dBA OA rating and 72 dBA FA rating

MM 15-4:
Site poles in clear space along the trail and roadway

MM 15-5:
Preparation of a vegetation removal plan

Project Memoranda and Non-Compliance Reports

No Project Memoranda or Non-Compliance Reports were issued during the period of February 2, 2002 to February 28, 2002.

cc:  
S. Lee; File (1224)

February, 2002
2

