## EPL
APPENDIX B
EQUIPMENT AND VEHICLE LIST
|  |  | Primary Equipment Description | CalEEMod Classification | Probable | Primary | Estimated Workforce | Quantity | Total | Total | Utilization | Horse-Power | Utilization | Project total |  |  | Paved | Total Trips | Avg Distance | % Paved Avg |  | Vendor Trip | Vendor Trip Distance | % paved
| # Crews | Stage |  |  | Fuel Type | Equipment |  |  | Schedule | Duration | (Hrs./Day) |  | (Hrs./Day) | Hrs | mil/day | VMT | %
[6 empty] | Quantity |  |  | (Days) | (Days)
01 Survey | 1 | 01 | Survey |  |  |  | 4 | 8 | 600 | 600 | [7 empty] | 0 | 0 | 0% |  | 2 | 30
| 1 |  | 1-Ton Truck, 4x4 | Onroad MD | Diesel | 2 |  | 2 | 600 | 600 | 10 |  | 10 |  | 30 | 36000 | 99%
02 Staging Areas | 1 | 02 | Staging Areas |  |  |  | 5 | 10 | 600 | 600 | [7 empty] | 2400 | 20 | 73.75% | 74 | 1 | 30
| 1 |  | R/T Forklift | Forklifts | Diesel | 1 |  | 1 | 600 | 600 | 5 | 350 | 5 | 3000
| 1 |  | Generator | Generator | Diesel | 1 |  | 1 | 600 | 600 | 10 | 45 | 10 | 6000
| 1 |  | 1-Ton Truck, 4x4 | Onroad MD | Diesel | 1 |  | 1 | 600 | 600 | 4 |  |  |  | 30 | 18000 | 99%
| 1 |  | Boom/Crane Truck | Onroad HHD | Diesel | 1 |  | 1 | 600 | 600 | 5 |  |  | 50 | 30 | 18000 | 90% | 2400 | 20 | 73.75%
| 1 |  | Water Truck | Onroad HHD | Diesel | 2 |  | 2 | 600 | 600 | 10 |  |  |  | 10 | 12000 | 10%
| 1 |  | Truck, Semi-Tractor | Onroad HHD | Diesel | 1 |  | 1 | 600 | 600 | 6 |  |  |  | 30 | 18000 | 100%
03 Road Work | 1 | 03 | Road Work |  |  |  | 6 | 12 | 6 | 6 | [7 empty] | 6 | 30 | 99% | 99 | 2 | 30
| 1 |  | Excavator | Excavators | Diesel | 1 |  | 1 | 6 | 6 | 10 | 300 | 10 | 60
| 1 |  | Backhoe/Front Loader | Tractors/Loaders/Backhoes | Diesel | 1 |  | 1 | 6 | 6 | 10 | 350 | 10 | 60
| 1 |  | Track Type Dozer | Tractors/Loaders/Backhoes | Diesel | 1 |  | 1 | 6 | 6 | 10 | 350 | 10 | 60
| 1 |  | Motor Grader | Graders | Diesel | 1 |  | 1 | 6 | 6 | 10 | 350 | 10 | 60
| 1 |  | Drum Type Compactor | Rollers | Diesel | 1 |  | 1 | 6 | 6 | 10 | 250 | 10 | 60
| 1 |  | 1-Ton Truck, 4x4 | Onroad MD | Diesel | 2 |  | 2 | 6 | 6 | 10 |  |  |  | 30 | 360 | 99%
| 1 |  | Water Truck | Onroad HHD | Diesel | 2 |  | 2 | 6 | 6 | 10 |  |  |  | 10 | 120 | 10% | 12 | 10 | 10%
| 1 |  | Lowboy Truck/Trailer | Onroad HHD | Diesel | 1 |  | 1 | 6 | 6 | 10 |  |  |  | 30 | 180 | 99% | 6 | 30 | 99%
04A Install TSP H-frame Foundations | 1 | 04A | Install TSP H-frame Foundations |  |  |  | 5 | 0 | 12 | 12 | [7 empty] | 36 | 16.6667 | 93.6% | 94 | 0 | #DIV/0!
| 1 |  | Auger Truck | Onroad HHD | Diesel | 1 |  | 1 | 12 | 12 | 10 | 500 | 10 |  | 30 | 360 | 90% | 36 | 16.6667 | 93.6%
| 1 |  | Concrete Mixer Truck | Onroad HHD | Diesel | 2 |  | 2 | 12 | 12 | 6 | 425 | 6 |  | 10 | 240 | 99%
04B Install TSP H-frame Foundations | 1 | 04B | Install TSP H-frame Foundations |  |  |  | 5 | 10 | 24 | 24 | [7 empty] | 72 | 23.3333 | 78.57% | 79 | 2 | 30
| 1 |  | Backhoe/Front Loader | Tractors/Loaders/Backhoes | Diesel | 1 |  | 1 | 24 | 24 | 10 | 200 | 10 | 240
| 1 |  | 3/4-Ton Truck, 4x4 | Onroad MD | Gas | 2 |  | 2 | 24 | 24 | 5 |  |  |  | 30 | 1440 | 99%
| 1 |  | Boom/Crane Truck | Onroad HHD | Diesel | 1 |  | 1 | 24 | 24 | 7 |  |  |  | 30 | 720 | 90% | 72 | 23.3333 | 78.57%
| 1 |  | Water Truck | Onroad HHD | Diesel | 1 |  | 1 | 24 | 24 | 10 |  |  |  | 10 | 240 | 10%
| 1 |  | Dump Truck | Onroad HHD | Diesel | 1 |  | 1 | 24 | 24 | 10 |  |  |  | 30 | 720 | 90%
05 TSP H-Frame Haul | 1 | 05 | TSP H-Frame Haul |  |  |  | 5 | 10 | 12 | 12 | [7 empty] | 48 | 25 | 87.4% | 87 | 2 | 30
| 1 |  | 3/4-Ton Truck, 4x4 | Onroad MD | Gas | 2 |  | 2 | 12 | 12 | 8 |  |  |  | 30 | 720 | 99%
| 1 |  | Boom/Crane Truck | Onroad HHD | Diesel | 1 |  | 1 | 12 | 12 | 8 |  |  |  | 30 | 360 | 90% | 48 | 25 | 87.4%
| 1 |  | Flat Bed Pole Truck | Onroad HHD | Diesel | 2 |  | 2 | 12 | 12 | 10 |  |  |  | 30 | 720 | 99%
| 1 |  | Water Truck | Onroad HHD | Diesel | 1 |  | 1 | 12 | 12 | 10 |  |  |  | 10 | 120 | 10%
06 TSP H-frame Assembly | 1 | 06 | TSP H-frame Assembly |  |  |  | 5 | 10 | 24 | 24 | [7 empty] | 48 | 20 | 70% | 70 | 4 | 30
| 1 |  | Compressor Trailer | Air Compressors | Diesel | 1 |  | 1 | 24 | 24 | 6 | 60 | 6 | 144
| 1 |  | 3/4-Ton Truck, 4x4 | Onroad MD | Gas | 2 |  | 2 | 24 | 24 | 6 |  |  |  | 30 | 1440 | 99%
| 1 |  | 1-Ton Truck, 4x4 | Onroad MD | Diesel | 2 |  | 2 | 24 | 24 | 6 |  |  |  | 30 | 1440 | 99%
| 1 |  | Boom/Crane Truck | Onroad HHD | Diesel | 1 |  | 1 | 24 | 24 | 7 |  |  |  | 30 | 720 | 90% | 48 | 20 | 70%
| 1 |  | Water Truck | Onroad HHD | Diesel | 1 |  | 1 | 24 | 24 | 10 |  |  |  | 10 | 240 | 10%
7A TSP H-frame Erection | 1 | 7A | TSP H-frame Erection |  |  |  | 5 | 0 | 8 | 8 | [7 empty] | 16 | 10 | 94.5% | 95 | 0 | #DIV/0!
| 1 |  | Jet A Fuel Truck | Onroad HHD | Diesel | 1 |  | 1 | 8 | 8 | 6 |  |  |  | 10 | 80 | 99% | 16 | 10 | 94.5%
| 1 |  | Helicopter Support Truck | Onroad HHD | Diesel | 1 |  | 1 | 8 | 8 | 6 |  |  |  | 10 | 80 | 90%
| 1 |  | Medium-duty Helicopter | Helicopter | Jet A | 1 |  | 1 | 8 | 8 | 4 |  | 6 | 32
7B TSP H-frame Erection | 1 | 7B | TSP H-frame Erection |  |  |  | 5 | 10 | 24 | 24 | [7 empty] | 24 | 10 | 10% | 10 | 2 | 30
| 1 |  | Compressor Trailer | Air Compressors | Diesel | 1 |  | 1 | 24 | 24 | 6 | 60 | 6 | 144
| 1 |  | R/T Crane | Cranes | Diesel | 1 |  | 1 | 24 | 24 | 7 | 350 | 7 | 168
| 1 |  | 3/4-Ton Truck, 4x4 | Onroad MD | Gas | 1 |  | 1 | 24 | 24 | 6 |  |  |  | 30 | 720 | 99%
| 1 |  | 1-Ton Truck, 4x4 | Onroad MD | Diesel | 1 |  | 1 | 24 | 24 | 6 |  |  |  | 30 | 720 | 99%
| 1 |  | Water Truck | Onroad HHD | Diesel | 1 |  | 1 | 24 | 24 | 10 |  |  |  | 10 | 240 | 10% | 24 | 10 | 10%
8A Install/Remove Conductor and Install OPGW | 2 | 8A | Install/Remove Conductor and Install OPGW |  |  |  | 20 | 0 | 103 | 51.5 | [10 empty] | 0 | 0 | #DIV/0!
| 2 |  | Backhoe/Front Loader | Tractors/Loaders/Backhoes | Diesel | 1 |  | 2 | 103 | 51.5 | 8 | 125 | 8 | 824
| 2 |  | Sock Line Puller | Other Construction Equipment | Diesel | 1 |  | 2 | 103 | 51.5 | 10 | 300 | 10 | 1030
| 2 |  | Conductor Splicing Rig | Other Construction Equipment | Diesel | 1 |  | 2 | 103 | 51.5 | 10 | 350 | 10 | 1030
| 2 |  | Fiber Splicing Lab | Other Construction Equipment | Diesel | 1 |  | 2 | 103 | 51.5 | 10 | 300 | 10 | 1030
8B Install/Remove Conductor and Install OPGW | 2 | 8B | Install/Remove Conductor and Install OPGW |  |  |  | 20 | 0 | 203 | 101.5 | [7 empty] | 812 | 5.5 | 94.91% | 95 | 0 | #DIV/0!
| 2 |  | Bull Wheel Puller | Other Construction Equipment | Diesel | 1 |  | 2 | 203 | 101.5 | 10 | 350 | 10 | 2030
| 2 |  | Wire Truck/Trailer | Onroad HHD | Diesel | 2 |  | 4 | 203 | 101.5 | 10 | 350 | 10 |  | 1 | 406 | 99% | 812 | 5.5 | 94.91%
| 2 |  | Jet A Fuel Truck | Onroad HHD | Diesel | 1 |  | 2 | 203 | 101.5 | 4 |  |  |  | 10 | 2030 | 99% |  | #DIV/0! | 94.5%
| 2 |  | Helicopter Support Truck | Onroad HHD | Diesel | 1 |  | 2 | 203 | 101.5 | 7 |  |  |  | 10 | 2030 | 90%
| 2 |  | Light Helicopter | Helicopter | Jet A | 1 |  | 2 | 203 | 101.5 | 7 |  | 7
8C Install/Remove Conductor and Install OPGW | 2 | 8C | Install/Remove Conductor and Install OPGW |  |  |  | 20 | 0 | 267 | 133.5 | [7 empty] | 267 | 30 | 0.9 | 90 | 6 | 30
| 2 |  | Dump Truck | Onroad HHD | Diesel | 1 |  | 2 | 267 | 133.5 | 10 |  |  |  | 30 | 8010 | 90% | 267 | 30 | 90%
8D Install/Remove Conductor and Install OPGW | 2 | 8D | Install/Remove Conductor and Install OPGW |  |  |  | 20 | 40 | 403 | 201.5 | [7 empty] | 3224 | 27.5 | 0.91545 | 92 | 4 | 30
| 2 |  | Hydraulic Rewind Puller | Other Construction Equipment | Diesel | 1 |  | 2 | 403 | 201.5 | 10 | 350 | 10 | 4030
| 2 |  | ¾-Ton Truck, 4x4 | Onroad MD | Gas | 1 |  | 2 | 403 | 201.5 | 10 |  |  |  | 30 | 12090 | 99%
| 2 |  | 1-Ton Truck, 4x4 | Onroad MD | Diesel | 2 |  | 4 | 403 | 201.5 | 10 |  |  |  | 30 | 24180 | 99%
| 2 |  | Static Truck/Tensioner | Onroad HHD | Diesel | 1 |  | 2 | 403 | 201.5 | 10 | 350 | 10 |  | 30 | 12090 | 90% | 3224 | 27.5 | 91.55%
| 2 |  | Manlift/Bucket Truck | Onroad HHD | Diesel | 1 |  | 2 | 403 | 201.5 | 10 |  |  |  | 30 | 12090 | 90%
| 2 |  | Boom/Crane Truck | Onroad HHD | Diesel | 1 |  | 2 | 403 | 201.5 | 10 |  |  |  | 30 | 12090 | 90%
| 2 |  | Truck, Semi-Tractor | Onroad HHD | Diesel | 2 |  | 4 | 403 | 201.5 | 10 |  |  |  | 30 | 24180 | 100%
| 2 |  | Lowboy Truck/Trailer | Onroad HHD | Diesel | 2 |  | 4 | 403 | 201.5 | 10 |  |  |  | 30 | 24180 | 99%
| 2 |  | Water Truck | Onroad HHD | Diesel | 1 |  | 2 | 403 | 201.5 | 10 |  |  |  | 10 | 4030 | 10%
9 Install/Remove Guard Structures | 1 | 9 | Install/Remove Guard Structures |  |  |  | 5 | 10 | 2 | 2 | [7 empty] | 10 | 26 | 85.92% | 86 | 4 | 30
| 1 |  | Compressor Trailer | Air Compressors | Diesel | 2 |  | 2 | 2 | 2 | 7 | 60 | 7 | 28
| 1 |  | Backhoe/Front Loader | Tractors/Loaders/Backhoes | Diesel | 1 |  | 1 | 2 | 2 | 10 | 125 | 10 | 20
| 1 |  | 3/4-Ton Truck, 4x4 | Onroad MD | Gas | 2 |  | 2 | 2 | 2 | 8 |  |  |  | 30 | 120 | 99%
| 1 |  | 1-Ton Truck, 4x4 | Onroad MD | Diesel | 2 |  | 2 | 2 | 2 | 8 |  |  |  | 30 | 120 | 99%
| 1 |  | Manlift/Bucket Truck | Onroad HHD | Diesel | 1 |  | 1 | 2 | 2 | 8 | 250 | 8 |  | 30 | 60 | 90% | 10 | 26 | 85.92%
| 1 |  | Boom/Crane Truck | Onroad HHD | Diesel | 1 |  | 1 | 2 | 2 | 10 | 350 | 10 |  | 30 | 60 | 90%
| 1 |  | Auger Truck | Onroad HHD | Diesel | 1 |  | 1 | 2 | 2 | 8 | 500 | 8 |  | 30 | 60 | 90%
| 1 |  | Water Truck | Onroad HHD | Diesel | 1 |  | 1 | 2 | 2 | 5 |  |  |  | 10 | 20 | 10%
| 1 |  | Extendable Flat Bed Pole Truck | Onroad HHD | Diesel | 1 |  | 1 | 2 | 2 | 8 |  |  |  | 30 | 60 | 99%
10A Modify Existing Structures | 1 | 10A | Modify Existing Structures |  |  |  | 5 | 0 | 11 | 11 | [7 empty] | 22 | 10 | 94.5% | 95 | 0 | #DIV/0!
| 1 |  | Jet A Fuel Truck | Onroad HHD | Diesel | 1 |  | 1 | 11 | 11 | 7 |  | 7 |  | 10 | 110 | 99% | 22 | 10 | 94.5%
| 1 |  | Helicopter Support Truck | Onroad HHD | Diesel | 1 |  | 1 | 11 | 11 | 7 |  | 7 |  | 10 | 110 | 90%
| 1 |  | Light Helicopter | Helicopter | Jet A | 1 |  | 1 | 11 | 11 | 7 |  | 7
10B Modify Existing Structures | 1 | 10B | Modify Existing Structures |  |  |  | 5 | 10 | 162 | 162 | [7 empty] | 486 | 30 | 90% | 90 | 2 | 30
| 1 |  | Compressor Trailer | Air Compressors | Diesel | 1 |  | 1 | 162 | 162 | 10 | 60 | 10 | 1620
| 1 |  | 3/4-Ton Truck, 4x4 | Onroad MD | Gas | 1 |  | 1 | 162 | 162 | 10 |  |  |  | 30 | 4860 | 99%
| 1 |  | 1-Ton Truck, 4x4 | Onroad MD | Diesel | 1 |  | 1 | 162 | 162 | 10 | 300 | 10 |  | 30 | 4860 | 99%
| 1 |  | Manlift/Bucket Truck | Onroad HHD | Diesel | 2 |  | 2 | 162 | 162 | 10 | 250 | 10 |  | 30 | 9720 | 90% | 486 | 30 | 90%
| 1 |  | Boom/Crane Truck | Onroad HHD | Diesel | 1 |  | 1 | 162 | 162 | 10 | 350 | 10 |  | 30 | 4860 | 90%
11 Restoration | 1 | 11 | Restoration |  |  |  | 7 | 14 | 180 | 180 | [7 empty] | 360 | 20 | 76.75% | 77 | 2 | 30
| 1 |  | Backhoe/Front Loader | Tractors/Loaders/Backhoes | Diesel | 1 |  | 1 | 180 | 180 | 4 | 125 | 4 | 720
| 1 |  | Motor Grader | Graders | Diesel | 1 |  | 1 | 180 | 180 | 6 | 250 | 6 | 1080
| 1 |  | Drum Type Compactor | Rollers | Diesel | 1 |  | 1 | 180 | 180 | 4 | 100 | 4 | 720
| 1 |  | 1-Ton Truck, 4x4 | Onroad MD | Diesel | 2 |  | 2 | 180 | 180 | 4 |  |  |  | 30 | 10800 | 99%
| 1 |  | Water Truck | Onroad HHD | Diesel | 1 |  | 1 | 180 | 180 | 8 |  |  |  | 10 | 1800 | 10% | 360 | 20 | 76.75%
| 1 |  | Lowboy Truck/Trailer | Onroad HHD | Diesel | 1 |  | 1 | 180 | 180 | 4 |  |  |  | 30 | 5400 | 99%
[9 empty] | TOTAL Days | 567.5
25.7955
506
0

## Equipment
Description | CalEEMod | Onroad Engine | Distance | Paved road
¾-Ton Truck, 4x4 | Onroad MD | MD | 30 | 0.99
1-Ton Truck | Onroad MD | MD | 30 | 0.99
1-Ton Truck, 4x4 | Onroad MD | MD | 30 | 0.99
22-Ton Manitex | Cranes
3/4-Ton Truck, 4x4 | Onroad MD | MD | 30 | 0.99
Auger Truck | Onroad HHD | HHD | 30 | 0.9
Backhoe/Front Loader | Tractors/Loaders/Backhoes
Blackhawk Helicopter | Helicopter
Boom/Crane Truck | Onroad HHD | HHD | 30 | 0.9
Bull Wheel Puller | Other Construction Equipment
Chipper | NA
Compressor Trailer | Air Compressors
Concrete Mixer Truck | Onroad HHD | HHD | 10 | 0.99
Concrete Truck | Onroad HHD | HHD | 10 | 0.99
Conductor Splicing Rig | Other Construction Equipment
Crew Bus | Onroad MD | MD | 100 | 0.99
D8 Cat | Tractors/Loaders/Backhoes
Drilling Rig | Bore/Drill Rigs
Drum Type Compactor | Rollers
Dump Truck | Onroad HHD | HHD | 30 | 0.9
Dump Truck, 4x4 | Onroad HHD | MD | 30 | 0.9
Excavator | Excavators
Extendable Flat Bed Pole Truck | Onroad HHD | HHD | 30 | 0.99
Fiber Splicing Lab | Other Construction Equipment
Flat Bed Pole Truck | Onroad HHD | HHD | 30 | 0.99
Flatbed Trailer | NA
Generator | Generator
Helicopter Support Truck | Onroad HHD | HHD | 10 | 0.9
Hughes 500 E Helicopter | Helicopter
Hydraulic Rewind Puller | Other Construction Equipment
Hydraulic Rewind Puller | Other Construction Equipment
Jet A Fuel Truck | Onroad HHD | HHD | 10 | 0.99
Light Helicopter | Helicopter
Lowboy Truck/Trailer | Onroad HHD | HHD | 30 | 0.99
Manlift/Bucket Truck | Onroad HHD | HHD | 30 | 0.9
Medium/Heavy-duty Helicopter | Helicopter
Medium-duty Helicopter | Helicopter
Motor Grader | Graders
Pipe Truck/Trailer | Onroad HHD | HHD | 30 | 0.99
R/T Crane | Cranes
R/T Crane (L) | Cranes
R/T Crane (M) | Cranes
R/T Forklift | Forklifts
Rubber Tire Backhoe | Rough Terrain Forklifts
Sag Cat w./ 2 winches | Tractors/Loaders/Backhoes
Sag D8 Cat w/2 winches | Tractors/Loaders/Backhoes
Sock Line Puller | Other Construction Equipment
Static Truck/Tensioner | Onroad HHD | HHD | 30 | 0.9
Stump Grinder | NA
Track Type Dozer | Tractors/Loaders/Backhoes
Tracked Excavator | Excavators
Truck, Semi-Tractor | Onroad HHD | HHD | 30 | 1
V-Groove Puller | Other Construction Equipment
Water Truck | Onroad HHD | HHD | 10 | 0.1
Wheel Loader | Tractors/Loaders/Backhoes
Wire Truck/Trailer | Onroad HHD | HHD | 1 | 0.99